## Sheet1
# | Task | Update Date | Assigned Person | Progress/ Note | next meeting | 2024-08-02
1 | Article & ticker & event labelling - human labelling | 2024-07-19 | ALL | Team each label 5 articles for 10 selected companies in industries and share some preliminary findings regarding rubric creation
2 | Event label - Generate keywords relevant to each event | 2024-08-02 | Ben | Ben has made some progress on it？ (explore.ipynb & keyed_data)
3 | Event label - Use extracted keywords to classify article | 2024-08-02 | Ben
4 | Event label - Use GPT api to generate preliminary labels | 2024-07-05 | Isabelle and Ella
5 | Event label - Refine GPT to provide confirmation using Che's event definition | Ongoing | Isabelle and Ella | Isabelle and Ella can refine current prompt
6 | Event label - Use BERT embeddings to identify relevant events for each article | Ongoing | Isabelle and ? | Embedding of event (using keywords from task 2) v.s. Embedding of article (from extracted keywords)
7 | Event label - Fine-tune BERT using labeled data |  | Harit
8 | Returns data - Study the time period (e.g. past 5 days, next 5 days) and characteristics to consider | 2024-08-02 | Ben | Ben has built functions on stock return stuff, implemented Ben's function into prompt
9 | Returns data - Obtain excess returns from the past 5 days, calculate self-correlation |  | Ben | Ben has built functions on stock return stuff
10 | Article & ticker & event labelling - refine stock return function to take into account of time | 2024-08-02 |  | implemented Ben's function into prompt
11 | Article & ticker & event labelling - ticker-company map | 2024-07-11 | Ella | SP500 company-ticker map v1 done
12 | Article & ticker & event labelling - rubric creation |  |  | After the above steps, we would potentially have a more refined prompt/pipeline, we can 1) generalize "human labelling" to include 5% randomized samples per industry, 2) assess and prepare for final prompt submission
13 | Article & ticker & event labelling - summarize annotated labellings | next meeting
14 | Article & ticker & event labelling - annotate randomized 5% articles | next meeting | ALL
15
16
17
18
19
20

## Industry Assignment
Industry | Person
Technology | Xuanzhong
Healthcare | Ella
Financials | Ben
Consumer Discretionary | Ishan
Energy | Isabelle
Industrials | Harit